## Tracker
N | Activity | Status | Completion (%)
1 | Project initiation and planning | Completed | 100
1.1 | Kick-off meeeting and scope statement sign-off | Completed | 100
1.2 | Budget estimation and approval | Completed | 100
1.3 | Hiring of team members | Completed | 100
2 | Architectural Design | Completed | 100
2.1 | Site visit and assessment | Completed | 100
2.2 | Project schedule development | Completed | 100
2.3 | Architectural and Structural design drafting | Completed | 100
2.4 | Design reviews with client | Completed | 100
2.5 | Finalize detailed architectural and structural drawings | Completed | 100
3 | Site Preparation | Completed | 100
3.1 | Site clearing | Completed | 100
3.2 | Land leveling | Completed | 100
3.3 | Site survey and installation of temporary facilities | Completed | 100
3.4 | Procurement of materials for foundation | Completed | 100
3.5 | Soil testing and reporting | Completed | 100
3.6 | Setting out the building print | Completed | 100
4 | Foundation | Completed | 100
4.1 | Excavation for foundation | Completed | 100
4.2 | Pouring and curing of blinding concrete | Completed | 100
4.3 | Reinforcement of footings | Completed | 100
4.4 | Column formwork | Completed | 100
4.5 | Foundation blockwork and pouring of concrete in columns | Completed | 100
4.6 | Backfilling | Completed | 100
4.7 | Curing | Completed | 100
5 | Structural work | Completed | 100
5.1 | Blockwork up to lintel level | Completed | 100
5.2 | Curing | Completed | 100
5.3 | Formwork and casting of lintel beams | Completed | 100
5.4 | Curing | Completed | 100
5.5 | Blockwork up to roof level | Completed | 100
5.6 | Curing | Completed | 100
5.7 | Procurement of roofing materials | Completed | 100
6 | Roofing | Completed | 100
6.1 | Roof truss fabrication and installation | Completed | 100
6.2 | Roof covering | Completed | 100
6.3 | Fascia board and gutter installation | Completed | 100
7 | Finishing | Ongoing | 40
7.1 | Fixing of windows | Completed | 100
7.2 | Ceiling installation and painting | Completed | 100
7.3 | Fixing of doors | Completed | 100
7.4 | Internal plastering and screeding | Completed | 100
7.5 | External plastering and screeding | Ongoing | 70
7.6 | Electrical Wiring | Ongoing | 30
7.7 | Plumbing | Ongoing | 40
7.8 | Tiling | Ongoing | 50
7.9 | Internal painting | Not Started | 0
7.1.0 | External painting | Not Started | 0
8 | Final site walkthrough and inspection | Not Started | 0
8.1 | Tiling cont'd | Not Started | 0
8.2 | Plumbing cont'd | Not Started | 0
8.3 | Electrical wiring cont'd | Not Started | 0
8.4 | Site cleaning | Not Started | 0
8.5 | Client orientation | Not Started | 0
8.6 | Handover and Signoff | Not Started | 0